## Cybersecurity
Information Security Risk-Aligned Framework | [8 empty] | Maturity Model | [6 empty] | Action Plan FY2016 |  |  |  | Action Plan FY2017 |  |  |  | Action Plan FY2018
Function | Category | InfoSec Service Catalog | Risk | CSC Top 20 | FY-18 $ | FY-19 $ | FY-20 $ | NIST Pol. | 0 | 1 | 2 | 3 | 4 | 5 | 6 | FY18-Q1 | FY18-Q2 | FY18-Q3 | FY18-Q4 | FY19-Q1 | FY19-Q2 | FY19-Q3 | FY19-Q4 | FY20-Q1 | FY20-Q2 | FY20-Q3 | FY20-Q4
Identify | Asset Management | Ops. Sec. - Asset Management - Physical and Environmental | 4 7 | 1,2 | $xxx $xxx |  |  | DI DM | [7 empty] | Action Plan FY2016 FY18-Q2: Asset Strategy; Action Plan FY2017 FY19-Q1: Review; Action Plan FY2018 FY20-Q1: Project 7A
| Business Environment | Governance - Regulatory, Legal, Compliance | All | - |  |  | $xxx | AP |  |  |  |  | Metrics |  |  | Action Plan FY2016 FY18-Q1: Risk Program
| Governance | Governance - Security Information Management | 5 | - | $xxx |  |  | AU PL PM | [7 empty] | Action Plan FY2016 FY18-Q2: Policy Dev.; Action Plan FY2017 FY19-Q4: Policy Review
| Risk Assessment | Security and Risk Assessments | 5a | 4 |  | $xxx | $xxx | AR | [7 empty] | Action Plan FY2016 FY18-Q2: Automate; Action Plan FY2016 FY18-Q3: Dashboard
| Risk Management | Governance - Risk Management | 5b | - |  |  |  | AR | [7 empty] | Action Plan FY2016 FY18-Q2: Integration 1; Action Plan FY2016 FY18-Q4: Integration 2; Action Plan FY2017 FY19-Q2: Integration 3; Action Plan FY2018 FY20-Q2: Review
| Supply Chain Risk Management | Vendor contract, Governance | All | -
Protect | Identity Management and Access Control | Identity and Access Management (IAM) - IAM - SSO - NAC - RBAC | 2 3 6 9 | 5, 9 11, 12 13, 14 15, 16 | $xxx $xxx $xxx $xxx | $xxx | $xxx | AC IA | [7 empty] | Action Plan FY2016 FY18-Q1: NAC; Action Plan FY2016 FY18-Q4: SSO - Phase 0; Action Plan FY2017 FY19-Q2: IAM; Action Plan FY2018 FY20-Q1: SSO - Phase 3
| Awareness and Training | Awareness and Training | 10 | 5,17 |  | $xxx |  | AT PS |  |  |  |  | Metrics |  |  | Action Plan FY2016 FY18-Q1: Alignment; Action Plan FY2017 FY19-Q1: Review; Action Plan FY2018 FY20-Q1: Review
| Data Security | Security Architecture and Design (Life Cycle) | 13 | 1,2 |  | $xxx |  | CA | [7 empty] | Action Plan FY2016 FY18-Q2: Report; Action Plan FY2017 FY19-Q2: Report; Action Plan FY2018 FY20-Q2: Report
| Information Protection Processes and Procedures | Governance - Proactive Protection - - Policies, Standards, Guidelines - ITSM Process governance and maturity - Acquisition, Development and Maintenance - Application development life cycle | 11 | 3, 4 7, 9 10, 11 18, 19 |  |  |  | MP PE SA SC |  |  |  |  | Metrics (e-discovery) |  |  | Action Plan FY2016 FY18-Q2: MDM; Action Plan FY2017 FY19-Q1: IT Service Management - Automation; Action Plan FY2018 FY20-Q1: Review
| Maintenance | Operations Security - Asset Maintenance | 14 | 3 ,4 5, 11 12 |  |  | $xxx | MA | [7 empty] | Action Plan FY2017 FY19-Q1: Asset Management; Action Plan FY2018 FY20-Q1: Full Asset Management
| Protective Technology | Operations Security - Change Management - Information Management and Encryption | 15 | 5, 6 7, 8 11, 13 14, 16 | $xxx | $xxx | $xxx | CM | [7 empty] | Action Plan FY2016 FY18-Q2: ITSM Align; Action Plan FY2017 FY19-Q1: Change Management; Action Plan FY2018 FY20-Q1: Review Change Mgmt.
Detect | Anomalies and Events | Monitor, Alerts and Reports - SIEM-Vuln PCI-PII-PHI | 1b | 6, 9 12, 19 | $xxx | $xxx | $xxx | SI |  |  |  |  | Metrics |  |  | Action Plan FY2016 FY18-Q2: Pen-Test; Action Plan FY2016 FY18-Q4: Pen-Test; Action Plan FY2017 FY19-Q1: External Pen-Test; Action Plan FY2017 FY19-Q3: Pen-Test; Action Plan FY2018 FY20-Q1: External Pen-Test; Action Plan FY2018 FY20-Q3: Pen-Test
| Security Continuous Monitoring | Monitor, Alerts and Reports | 1a | 4, 8 16, 19 |  | $xxx | $xxx | [8 empty] | Action Plan FY2016 FY18-Q1: Expand 3; Action Plan FY2017 FY19-Q1: Expand 4; Action Plan FY2018 FY20-Q1: Expand 5
| Detection Processes | Monitor, Alerts and Reports - DLP | 1 | 19 | $xxx $xxx | $xxx | $xxx | [8 empty] | Action Plan FY2016 FY18-Q3: DLP Phase 2; Action Plan FY2017 FY19-Q1: DLP Phase 3
Respond | Response Planning | Gov. - Bus. Impact Analysis | 5c | 19 | [11 empty] | Action Plan FY2016 FY18-Q1: BIA - Phase 1; Action Plan FY2017 FY19-Q1: BIA - Phase 3
| Communications | Incident Response - Alignment | 8d | 19 | [11 empty] | Action Plan FY2016 FY18-Q1: Architecture; Action Plan FY2017 FY19-Q1: Process Mapping
| Analysis | Incident Response - Risk | 8a | 6,19 | $xxx | [10 empty] | Action Plan FY2016 FY18-Q1: Risk Mapping; Action Plan FY2016 FY18-Q3: Formal Review; Action Plan FY2017 FY19-Q3: Formal Review
| Mitigation | Incident Response | 8c | 4,19 |  |  |  | IR | [7 empty] | Action Plan FY2016 FY18-Q3: CIRT Test 1; Action Plan FY2017 FY19-Q1: CIRT Full Test; Action Plan FY2018 FY20-Q3: CIRT Test 3
| Improvements | Incident Response - Maturity | 8e | 19,20 | $xxx | [10 empty] | Action Plan FY2016 FY18-Q1: External Risk Assessment; Action Plan FY2016 FY18-Q2: Remediate; Action Plan FY2017 FY19-Q1: External Risk Assessment; Action Plan FY2018 FY20-Q3: Remediate
Recover | Recovery Planning | Ops. Security - Bus. Continuity | 8 | 10 |  | $xxx | $xxx | CP | [7 empty] | Action Plan FY2016 FY18-Q3: DR Plan; Action Plan FY2017 FY19-Q1: Test BC Plan; Action Plan FY2018 FY20-Q1: Test BC Plan
| Improvements | Ops. Security - Downtime Mgmt. | 8b | 20 | [11 empty] | Action Plan FY2016 FY18-Q1: Document; Action Plan FY2016 FY18-Q3: Standardize Training; Action Plan FY2017 FY19-Q1: Test Downtime Plan; Action Plan FY2018 FY20-Q1: Test Downtime Plan
| Communications | Ops. Security - Svc. Alignment | 12 | - | $xxx | [10 empty] | Action Plan FY2016 FY18-Q1: LMS Review; Action Plan FY2016 FY18-Q3: Mid-year; Action Plan FY2017 FY19-Q1: LMS Review; Action Plan FY2017 FY19-Q3: Mid-year; Action Plan FY2018 FY20-Q1: LMS Review; Action Plan FY2018 FY20-Q3: Mid-year
NIST Functions
Risk Priorities & Appetite - Internal/External metrics
Service Catalog
Budgets:
Funded - Unfunded - Proposed -
Policy Alignment
"Tiers" -
Maturity Map
Three (or more) Year Action Plan - NIST "Profiles" by Quarter
Sample Projects and Initiatives
CMM -metrics
Challenges identified
Maturity - progress identified
Key initiatives nested and aligned
NIST Cybersecurity Framework, adapted by Christopher Paidhrin, CISSP, CRISC https://www.linkedin.com/in/venturabrian
Revision 7.1 - 2013-2018
Current State
Future State
NIST Cybersecurity
Enterprise-Aligned
Framework:
- Risks
- Service
Catalog
- Priorities
- Maturity
- Metrics
- 3-Year
Project,
Program &
Initiative
Roadmap
IT Service Management
Life-Cycle
Process
Improvement
Aligned Standards
Continuous Process and Service Improvement
Business View / Priorities / Risk-Alignment

## Guide - Index
OrgName - Information Security Risk-Aligned Framework | [9 empty] | Maturity Roadmap FY2016 | [6 empty] | Action Plan FY2016 | [5 empty] | Action Plan FY2017 |  |  |  | Action Plan FY2018
Function | Category Unique Identifier | Category | InfoSec Service Catalog | Risk Rank | CSC Top Twenty | FY2018 $ | FY2019 $ | FY2020 $ | NIST Policy Family | 0 Basic | 1 Controlled | 2 Standards | 3 Rational | 4 Virtual | 5 Service | 6 Dynamic | FY2018-Q3 | FY2018-Q4 | FY2019-Q1 | FY2019-Q2 | FY2019-Q3 | FY2019-Q4 | FY2020-Q1 | FY2020-Q2 | FY2020-Q3 | FY2020-Q4 | FY2021-Q1 | FY2021-Q2 | FY2021-Q3 | FY2021-Q4
Identify | AM | Asset Management | Operations Security - Asset Management - Physical and Environmental | 4 7 | 1,2 | $xxx $xxx |  |  | DI DM | [8 empty] | Asset Inv. |  | Asset Strategy |  |  | Review |  |  |  | Project 7A
| BE | Business Environment | Governance - Regulatory, Legal, Compliance | All | - |  |  | $xxx | AP |  |  |  |  | Metrics |  |  | PCI, HIPAA | PII | Risk Program |  |  |  | Risk Program Review
| GV | Governance | Governance - Security Information Management | 5 | - | $xxx |  |  | AU PL PM | [7 empty] | Gov. Model |  |  | Policy Dev. | Policy Dev. | Policy Review |  |  |  | Policy Review |  |  |  | Policy Review
| RA | Risk Assessment | Security and Risk Assessments | 5a | 4 |  | $xxx | $xxx | AR | [7 empty] | RA Prog. | Upgrade |  | Automate | Dashboard
| RM | Risk Management | Governance - Risk Management | 5b | - |  |  |  | AR | [7 empty] | Framework | Review | Alignment | Integration 1 |  | Integration 2 |  | Integration 3 |  | Integration 4 |  | Review
| SC | Supply Chain Risk Management | Vendor contract, Governance |  | - |  | $xxx
Protect | AC | Identity Management and Access Control | Identity and Access Management (IAM) - IAM - SSO - NAC - RBAC | 2 3 6 9 | 5, 9 11, 12 13, 14 15, 16 | $xxx $xxx $xxx $xxx | $xxx | $xxx | AC IA | [8 empty] | NAC Plan | NAC | IAM Plan |  | SSO - Phase 0 | SSO - Phase 1 | IAM | SSO-Phase 2 |  | SSO - Phase 3 |  |  | SSO- Review
| AT | Awareness and Training | Awareness and Training | 10 | 5,17 |  | $xxx |  | AT PS |  |  |  |  | Metrics |  |  | Orientation |  | Alignment |  |  |  | Review |  |  |  | Review
| DS | Data Security | Security Architecture and Design (Life Cycle) | 13 | 1,2 |  | $xxx |  | CA | [7 empty] | Standards |  | Review Board | Report |  |  |  | Report |  |  |  | Report
| IP | Information Protection Processes and Procedures | Governance - Proactive Protection - - Policies, Standards, Guidelines - ITSM Process governance and maturity - Acquisition, Development and Maintenance - Application development life cycle | 11 | 3, 4 7, 9 10, 11 18, 19 |  |  |  | MP PE SA SC |  |  |  |  | Metrics (e-discovery) |  |  | Policies | Standards Baselines "Cloud" |  | MDM |  |  | IT Service Management - Automation |  |  |  | Review
| MA | Maintenance | Operations Security - Asset Maintenance | 14 | 3 ,4 5, 11 12 |  |  | $xxx | MA | [7 empty] | Asset Plan |  | Biomedical |  |  |  | Asset Management |  |  |  | Full Asset Management
| PT | Protective Technology | Operations Security - Change Management - Information Management and Encryption | 15 | 5, 6 7, 8 11, 13 14, 16 | $xxx | $xxx | $xxx | CM | [8 empty] | ITSM Review | ITSM Design | ITSM Align |  |  | Change Management |  |  |  | Review Change Mgmt.
Detect | AE | Anomalies and Events | Monitor, Alerts and Reports - SIEM-Vuln PCI-PII-PHI | 1b | 6, 9 12, 19 | $xxx | $xxx | $xxx | SI |  |  |  |  | Metrics |  |  | Pen-Test | Pen-Test | Pen-Test | Pen-Test | Pen-Test | Pen-Test | External Pen-Test | Pen-Test | Pen-Test | Pen-Test | External Pen-Test | Pen-Test | Pen-Test | Pen-Test
| CM | Security Continuous Monitoring | Monitor, Alerts and Reports | 1a | 4, 8 16, 19 |  | $xxx | $xxx | [8 empty] | Plan | Automation | Expand 3 |  |  |  | Expand 4 |  |  |  | Expand 5
| DP | Detection Processes | Monitor, Alerts and Reports - DLP | 1 | 19 | $xxx $xxx | $xxx | $xxx | [5 empty] | Metrics |  |  |  | DLP | DLP Go-Live |  | DLP Phase 2 |  | DLP Phase 3
Respond | RP | Response Planning | Governance - Business Impact Analysis | 5c | 19 | [8 empty] | Metrics |  |  |  |  | BIA - Phase 1 |  | BIA - Phase 2 |  | BIA - Phase 3
| CO | Communications | Incident Response - Service Alignment | 8d | 19 | [8 empty] | Metrics |  |  |  |  | Architecture |  | Workflow |  | Process Mapping
| AN | Analysis | Incident Response - Risk Analysis | 8a | 6,19 | $xxx | [12 empty] | Risk Mapping |  | Formal Review |  |  |  | Formal Review |  |  |  | Formal Review
| MI | Mitigation | Incident Response | 8c | 4,19 |  |  |  | IR | [9 empty] | CIRT Team |  | CIRT Test 1 |  | CIRT Full Test |  | CIRT Test 2 |  | CIRT Full Test |  | CIRT Test 3
| IM | Improvements | Incident Response - Maturity | 8e | 19,20 | $xxx | [10 empty] | Review | Remediate | External Risk Assessment | Remediate | Remediate | Remediate | External Risk Assessment | Remediate | Remediate | Remediate | External Risk Assessment | Remediate | Remediate | Remediate
Recover | RP | Recovery Planning | Ops. Security - Bus. Continuity | 8 | 10 |  | $xxx | $xxx | CP | [9 empty] | Test BC Plan | Process Alignment | DR Plan | Formalize Update | Test BC Plan |  | Mid-year |  | Test BC Plan |  | Mid-year
| IM | Improvements | Ops. Security - Downtime Mgmt. | 8b | 20 | [13 empty] | Document |  | Standardize Training |  | Test Downtime Plan |  |  |  | Test Downtime Plan
| CO | Communications | Ops. Security - Svc. Alignment | 12 | - | $xxx | [7 empty] | Metrics |  |  | Major Programs | Education | LMS Review |  | Mid-year |  | LMS Review |  | Mid-year |  | LMS Review |  | Mid-year
|  |  | Rev. 5.0 | [7 empty] | Current State |  |  | Progress Areas
|  |  | 2015-11-01 | [7 empty] | Future State |  |  | Challenge Areas
Functions
Cat. IDs
Risk Priorities & Appetite - Internal/External metrics
Sub-Category - Service Catalog
Funded - Unfunded - Proposed
Policy Alignment
"Tiers" or Maturity Map (see legend)
Hidden NIST Core Info. References
Three Year (or more) Action Plan (Implementation) based on "Profiles" -- Identified Risks, Priorities, Maturity, and Capabilities. Quarter-by-quarter initiative or project time-lines and measures of success
Sample Projects and Initiatives
CMM and metrics agnostic
Budget numbers are easily hidden
Challenges across services are readily identified
Maturity and progress also identified
Key initiatives nested and aligned
Maturity level of "Relational" or "Managed" (3, or mid-line) is 'realistic' near-term goal
NIST Cybersecurity Framework, adapted by Christopher Paidhrin, CISSP, CRISC https://www.linkedin.com/in/christopherpaidhrin
Revision 7.0 - 2013-2016

## NIST Framework (sample)
OrgName - Information Security Risk-Aligned Framework | [9 empty] | Maturity Roadmap FY2016 | [6 empty] | Action Plan FY2016 | [5 empty] | Action Plan FY2017 |  |  |  | Action Plan FY2018
Function | Category Unique Identifier | Category | InfoSec Service Catalog | Risk Rank | CSC Top Twenty | FY2018 $ | FY2019 $ | FY2020 $ | NIST Policy Family | 0 Basic | 1 Controlled | 2 Standards | 3 Rational | 4 Virtual | 5 Service | 6 Dynamic | FY2018-Q3 | FY2018-Q4 | FY2019-Q1 | FY2019-Q2 | FY2019-Q3 | FY2019-Q4 | FY2020-Q1 | FY2020-Q2 | FY2020-Q3 | FY2020-Q4 | FY2021-Q1 | FY2021-Q2 | FY2021-Q3 | FY2021-Q4
Identify | AM | Asset Management | Operations Security - Asset Management - Physical and Environmental | 4 7 | 1,2 | $xxx $xxx |  |  | DI DM | [8 empty] | Asset Inv. |  | Asset Strategy |  |  | Review |  |  |  | Project 7A
| BE | Business Environment | Governance - Regulatory, Legal, Compliance | All | - |  |  | $xxx | AP |  |  |  |  | Metrics |  |  | PCI, HIPAA | PII | Risk Program |  |  |  | Risk Program Review
| GV | Governance | Governance - Security Information Management | 5 | - | $xxx |  |  | AU PL PM | [7 empty] | Gov. Model |  |  | Policy Dev. | Policy Dev. | Policy Review |  |  |  | Policy Review |  |  |  | Policy Review
| RA | Risk Assessment | Security and Risk Assessments | 5a | 4 |  | $xxx | $xxx | AR | [7 empty] | RA Prog. | Upgrade |  | Automate | Dashboard
| RM | Risk Management | Governance - Risk Management | 5b | - |  |  |  | AR | [7 empty] | Framework | Review | Alignment | Integration 1 |  | Integration 2 |  | Integration 3 |  | Integration 4 |  | Review
| SC | Supply Chain Risk Management | Vendor contract, Governance |  | - |  | $xxx
Protect | AC | Identity Management and Access Control | Identity and Access Management (IAM) - IAM - SSO - NAC - RBAC | 2 3 6 9 | 5, 9 11, 12 13, 14 15, 16 | $xxx $xxx $xxx $xxx | $xxx | $xxx | AC IA | [8 empty] | NAC Plan | NAC | IAM Plan |  | SSO - Phase 0 | SSO - Phase 1 | IAM | SSO-Phase 2 |  | SSO - Phase 3 |  |  | SSO- Review
| AT | Awareness and Training | Awareness and Training | 10 | 5,17 |  | $xxx |  | AT PS |  |  |  |  | Metrics |  |  | Orientation |  | Alignment |  |  |  | Review |  |  |  | Review
| DS | Data Security | Security Architecture and Design (Life Cycle) | 13 | 1,2 |  | $xxx |  | CA | [7 empty] | Standards |  | Review Board | Report |  |  |  | Report |  |  |  | Report
| IP | Information Protection Processes and Procedures | Governance - Proactive Protection - - Policies, Standards, Guidelines - ITSM Process governance and maturity - Acquisition, Development and Maintenance - Application development life cycle | 11 | 3, 4 7, 9 10, 11 18, 19 |  |  |  | MP PE SA SC |  |  |  |  | Metrics (e-discovery) |  |  | Policies | Standards Baselines "Cloud" |  | MDM |  |  | IT Service Management - Automation |  |  |  | Review
| MA | Maintenance | Operations Security - Asset Maintenance | 14 | 3 ,4 5, 11 12 |  |  | $xxx | MA | [7 empty] | Asset Plan |  | Video Monitoring |  |  |  | Asset Management |  |  |  | Full Asset Management
| PT | Protective Technology | Operations Security - Change Management - Information Management and Encryption | 15 | 5, 6 7, 8 11, 13 14, 16 | $xxx | $xxx | $xxx | CM | [8 empty] | ITSM Review | ITSM Design | ITSM Align |  |  | Change Management |  |  |  | Review Change Mgmt.
Detect | AE | Anomalies and Events | Monitor, Alerts and Reports - SIEM-Vuln PCI-PII-PHI | 1b | 6, 9 12, 19 | $xxx | $xxx | $xxx | SI |  |  |  |  | Metrics |  |  | Pen-Test | Pen-Test | Pen-Test | Pen-Test | Pen-Test | Pen-Test | External Pen-Test | Pen-Test | Pen-Test | Pen-Test | External Pen-Test | Pen-Test | Pen-Test | Pen-Test
| CM | Security Continuous Monitoring | Monitor, Alerts and Reports | 1a | 4, 8 16, 19 |  | $xxx | $xxx | [8 empty] | Plan | Automation | Expand 3 |  |  |  | Expand 4 |  |  |  | Expand 5
| DP | Detection Processes | Monitor, Alerts and Reports - DLP | 1 | 19 | $xxx $xxx | $xxx | $xxx | [5 empty] | Metrics |  |  |  | DLP | DLP Go-Live |  | DLP Phase 2 |  | DLP Phase 3
Respond | RP | Response Planning | Governance - Business Impact Analysis | 5c | 19 | [8 empty] | Metrics |  |  |  |  | BIA - Phase 1 |  | BIA - Phase 2 |  | BIA - Phase 3
| CO | Communications | Incident Response - Service Alignment | 8d | 19 | [8 empty] | Metrics |  |  |  |  | Architecture |  | Workflow |  | Process Mapping
| AN | Analysis | Incident Response - Risk Analysis | 8a | 6,19 | $xxx | [12 empty] | Risk Mapping |  | Formal Review |  |  |  | Formal Review |  |  |  | Formal Review
| MI | Mitigation | Incident Response | 8c | 4,19 |  |  |  | IR | [9 empty] | CIRT Team |  | CIRT Test 1 |  | CIRT Full Test |  | CIRT Test 2 |  | CIRT Full Test |  | CIRT Test 3
| IM | Improvements | Incident Response - Maturity | 8e | 19,20 | $xxx | [10 empty] | Review | Remediate | External Risk Assessment | Remediate | Remediate | Remediate | External Risk Assessment | Remediate | Remediate | Remediate | External Risk Assessment | Remediate | Remediate | Remediate
Recover | RP | Recovery Planning | Ops. Security - Bus. Continuity | 8 | 10 |  | $xxx | $xxx | CP | [9 empty] | Test BC Plan | Process Alignment | DR Plan | Formalize Update | Test BC Plan |  | Mid-year |  | Test BC Plan |  | Mid-year
| IM | Improvements | Ops. Security - Downtime Mgmt. | 8b | 20 | [13 empty] | Document |  | Standardize Training |  | Test Downtime Plan |  |  |  | Test Downtime Plan
| CO | Communications | Ops. Security - Svc. Alignment | 12 | - | $xxx | [7 empty] | Metrics |  |  | Major Programs | Education | LMS Review |  | Mid-year |  | LMS Review |  | Mid-year |  | LMS Review |  | Mid-year
|  |  | Rev. 7.0 | [7 empty] | Current State |  |  | Progress Areas
|  |  | 2016-06-01 | [7 empty] | Future State |  |  | Challenge Areas

## NIST Framework v1.1
City of Portland - Information Security Risk-Aligned Framework | [13 empty] | Maturity Roadmap FY2016 |  |  |  |  | Action Plan FY2018-2019 |  |  |  | Action Plan FY2017-2018 |  |  |  | Action Plan FY2018-2019 |  |  |  | Action Plan FY2019-2020 |  |  |  | Action Plan FY2020-2021
Function | Category Unique Identifier | InfoSec Process Owner | InfoSec Backup | Category | InfoSec Service Catalog | Risk Rank | CSC Top Twenty | FY2016 $ | FY2017 $ | FY2018 $ | FY2019 $ | FY2020 $ | NIST Policy Family | 1 Initial | 2 Repeatable | 3 Defined | 4 Managed | 5 Optimizing | FY2018-Q3 | FY2018-Q4 | FY2019-Q1 | FY2019-Q2 | FY2019-Q3 | FY2019-Q4 | FY2020-Q1 | FY2020-Q2 | FY2020-Q3 | FY2020-Q4 | FY2021-Q1 | FY2021-Q2 | FY2021-Q3 | FY2021-Q4 | FY2022-Q1 | FY2022-Q2 | FY2022-Q3 | FY2022-Q4 | FY2023-Q1 | FY2023-Q2
Identify | AM | JS | BV | Asset Management | Operational Security - Asset Management | 3 | 1, 2 | [5 empty] | DI DM
- Device Inventory
- Software/Application Inventory
- Environment and Data Flow Diagrams
- Cloud Service and Technology Partner Inventories
| BE | Team | DM | Business Environment | Strategic Security - Governance | 5 | - | [5 empty] | AP
- Organizational Role
- Critical Infrastructure Identification
- Organizational Priorities
| GV | CAP | DM | Governance | Strategic Security - Governance and Compliance | 1 | - | [5 empty] | AU PL PM
[5 empty] | - Security Roles and Responsibilities | [14 empty] | Review Roles |  |  |  | Review Roles |  |  |  | Review Roles |  |  |  | Review Roles |  |  |  | Review Roles
[5 empty] | - Enterprise Security Policy | [14 empty] | Review Policies |  | Redesign - All |  | Review Policies |  |  |  | Review Policies |  |  |  | Review Policies |  |  |  | Review Policies
[5 empty] | - Enterprise Data Security Standards |  |  | 250000 | 100000 | 100000 | 100000 | 100000 | [7 empty] | GRC Framework | Research-Evaluation | Project Activation | Phase I | Phase I | Phase II | Phase II | Phase III | Phase III | Phase IV | Phase IV | Review
[5 empty] | - Compliance (PCI, PHI, FTI, CJIS, PII, Enterprise Standards) | [14 empty] | FTI SSR | PCI Assessment |  |  | FTI SSR | PCI Assessment |  |  | FTI SSR | PCI Assessment |  |  | FTI SSR | PCI Assessment |  |  | FTI SSR | PCI Assessment
| RA | DM | Team | Risk Assessment | Strategic Security - Risk Assessments | 11 | 4 | [5 empty] | AR
[5 empty] | - Risk Assessments | [15 empty] | CHD Assessments |  |  |  | CHD Assessments |  |  |  | CHD Assessments |  |  |  | CHD Assessments |  |  |  | CHD Assessments
| RM | CAP | BV | Risk Management | Strategic Security - Risk Management | 7 | - | [5 empty] | AR RM PM
[5 empty] | - Risk Management | [13 empty] | Review Risk Process |  |  |  | Review Risk Process |  |  |  | Review Risk Process |  |  |  | Review Risk Process |  |  |  | Review Risk Process
[5 empty] | - Risk Tolerance | [13 empty] | Review Tolerance |  |  |  | Review Tolerance |  |  |  | Review Tolerance |  |  |  | Review Tolerance |  |  |  | Review Tolerance
- Exception Management
| SC | CAP | BV | Supply Chain Risk Management | Vendor contract, Governance |  | - | [5 empty] | SA
Protect | AC | DM | JS | Identity Management and Access Control | Operational Security - Access Control |  | 5, 9 11, 12 13, 14 15, 16 | [5 empty] | AC IA
[5 empty] | - Account Management | 9 |  | 200000 | 20000 | 20000 | 20000 | 20000 | [9 empty] | IAM
[5 empty] | - Physical Access Controls |  |  | 0 | 100000 | 100000 | 50000 | 50000
[5 empty] | - Remote Access Controls |  |  | 155000 | 50000 | 20000 | 20000 | 75000
[5 empty] | - Principle of Least Privilege | [16 empty] | RBAC
- Network Segmentation
[5 empty] | - Network Security |  |  | 100000 | 70000 | 70000 | 70000 | 120000
[5 empty] | - Content Filtering |  |  | 0 | 0 | 0 | 300000 | 0 | [8 empty] | SWG Refresh
| AT | BV | JS | Awareness and Training | Strategic Security - Awareness and Training | 12 | 5, 17 | [5 empty] | AT PS
[5 empty] | - End-user Education | [15 empty] | PCI Education | General Education |  |  | Review |  |  |  | Review |  |  |  | Review |  |  |  | Review
- End-user Roles and Responsibilities
- Third Party Roles and Responsibilities
| DS | DM | BV | Data Security | Operational Security - Encryption and Data Integrity | 14 | 1, 2 13 14 18 | [5 empty] | CA
- Data Encryption at Rest
- Data Encryption in Transit
- Asset Disposal
- Data Loss Prevention
- File and System Integrity
- Separate Development from Production Environments
| IP | JS | DM | Information Protection Processes and Procedures | Operational Security - Processes and Procedures | 2 | 3, 4 7, 9 10, 11 18, 19 | [5 empty] | MP PE SA SC
- Baseline Configurations
- Software Development Life Cycle
- Change Control Process
- Backup/Restore Validation
- Data Retention and Destruction
- Metrics and Measuring
[5 empty] | - Vulnerability Management Plan | [17 empty] | Document Plan |  |  |  | Review Plan |  |  |  | Review Plan |  |  |  | Review Plan
[5 empty] | - Patch Management Plan | [18 empty] | Document Plan |  |  |  | Review Plan |  |  |  | Review Plan |  |  |  | Review Plan
| MA | DM | Team | Maintenance | Operational Security - Asset Maintenance | 4 | 3 ,4 5, 11 12 | [5 empty] | MA
- Asset Maintenance and Repair
| PT | JS | BV | Protective Technology | Operational Security - Protect Assets | 16 | 5, 6 7, 8 11, 13 14, 16 | [5 empty] | CM
- Audit Log Management
- Removable Media Controls
- System Access Control
[5 empty] | - Network and Wireless Intrusion Prevention |  |  | 0 | 175000 | 10000 | 15000 | 15000
Detect | AE | JS | BV | Anomalies and Events | Operational Security - Monitor, Analyze and Detect Events | 10 | 6, 9 12, 19 | [5 empty] | SI
[5 empty] | - Traffic Baselining | [17 empty] | Network Analytics
[5 empty] | - Event Management |  |  | 20000 | 20000 | 35000 | 150000 | 35000
| CM | JS | BV | Security Continuous Monitoring | - Monitor Network Controls for Events | 6 | 4, 8 16, 19
- Monitor Physical Controls for Events
- Monitor Employees for Events
- Monitor for Malware
- Monitor Third Party Activity
- Monitor Unauthorized Connections
- Internal Vulnerability Assessments
[5 empty] | - External Vulnerability Assessments |  |  | 55000 | 20000 | 60000 | 25000 | 65000
| DP | JS | BV | Detection Processes | - Detection Roles and Responsibilties | 15 | 6, 12
- Detection Process Testing
- Proper Communication Plan
- Continual Improvement
Respond | RP | BV | DM | Response Planning | Strategic Security - Incident Response | 8 | 19
[5 empty] | - Execute Response Plan During Events | [15 empty] | Finalize IR Plan |  |  |  | Review IR Plan |  |  |  | Review IR Plan |  |  |  | Review IR Plan |  |  |  | Review IR Plan
| CO | BV | DM | Communications | - Roles and Responsibilities Education | 18 | 19
- Consistent Incident Reporting
- Incident Response Tabletop Exercises
| AN | BV | DM | Analysis | - Events Consistently Investigated | 19 | 6, 19
- Event Impacts Understood
- Forensic Capabilities
| MI | BV | DM | Mitigation | - Incidents Contained | 13 | 4, 19 | [5 empty] | IR
- Incidents Mitigated
| IM-D | BV | DM | Improvements | - Response Plan Continual Improvement | 17 | 19, 20
- Strategies Updated
Recover | RP | DM | JS | Recovery Planning | Strategic Security - Business Continuity | 20 | 10 | [5 empty] | CP
- Execute Recovery Plan During Events
| IM-R | DM | JS | Improvements | - Recovery Plan Continual Improvement | 21 | 20
[5 empty] | - Strategies Updated |  |  | 100000 | 0 | 0 | 0 | 0
| CO | DM | JS | Communications | - Manage Public Relations | 22 | -
- Repair Reputation During Events
[5 empty] | Rev. 8.0 | [9 empty] | Current State |  |  | Progress Areas
[5 empty] | 2016-05-02 | [9 empty] | Future State |  |  | Challenge Areas
Note on I5: Paidhrin, Christopher: Asset mgmt. is both hardware and software.
Note on R5: Musson, Dean: ad hoc and reactive management of device and application inventory systems environment diagrams more complete than data flow diagrams totality of cloud services unknown
Note on R10: Musson, Dean: infosec role not clear or defined critical infrastructure not identified and cataloged organizational priorities seem shifting and inconsistent
Note on R14: Musson, Dean: security roles and responsibilities not well defined and without authority enterprise security policy requires rework enterprise data security standard does not exist compliance with pci successful as ad hoc project; fti has repeatable processes; other compliance largely ignored
Note on L17: Musson, Dean: CIP # 1 NIST Cybersecurity Framework
Note on S19: Musson, Dean: risk assessments performed as necessary for compliance repeatable risk assessment process documented
Note on S21: Musson, Dean: risk assessment process updated as part of process improvement risk tolerance loosely set at medium- exceptions managed ad hoc without defined process
Note on R27: Musson, Dean: AD management adhoc and reactive principle of least privilege not followed network largely unsegmented firewalls managed consistently; documented processes may not be complete content filtering project in jeopardy
Note on L28: Musson, Dean: CIP # 6 2FA Refresh
Note on L29: Paidhrin, Christopher: CIP # 8 SmartCard Tech. for compliance
Note on L30: Musson, Dean: CIP # 3 VPN Tech. Refresh
Note on L33: Paidhrin, Christopher: CIP # 2 Firewall Refresh
Note on L34: Paidhrin, Christopher: CIP # 9 Web Filtering
Note on R35: Musson, Dean: security awareness on the rise but processes remain undocumented no consistent delivery of theme or material roles and responsibilities not well defined or socialized third party roles and responsibilities not defined or socialized
Note on R39: Musson, Dean: data generally not encrypted at rest data generally not encrypted in transit asset disposal ensures media destruction for servers, workstations, and laptops, but asset disposal of mobile devices unknown; documentation unknown no data loss prevention controls in place file and system integrity controls are adhoc and reactive development environments not always separated from production environments; no policy
Note on R46: Musson, Dean: partial baseline configurations built for endpoints and servers, but not for other devices SDLC is performed adhoc and inconsistently between developer groups change control process is documented, centralized and managed within BTS restore validation is adhoc and reactive primitive metrics exist vulnerability management plan not documented patch management process is reactive; delivery typically within 30 days; some assets not patched; some documented processes exist
Note on S55: Musson, Dean: consistent tools and processes typically used among support staff KCS to be implemented soon
Note on R57: Musson, Dean: audit log collection is inconsistent across platforms removable media not prohibited system access controls adhoc and reactive intrusion prevention managed reactively
Note on L61: Musson, Dean: CIP #10 - Wireless IPS
Note on R62: Musson, Dean: traffic is not baselined for anomaly comparison siem is collecting some events from a small group of devices; no strategy or processes defined graylog to be implemented soon
Note on L64: Paidhrin, Christopher: CIP #5 SIM Expansion
Note on R65: Musson, Dean: monitoring not consistently performed minimal alerting of events anti-malware largely managed reactively vulnerability assessment process not documented vulnerability assessments largely ignored by operational staff; no process or policy reaction to external vulnerability assessments may be slow or absent all together; no process or policy
Note on L72: Paidhrin, Christopher: CIP # 7 Citywide InfoSec External Assessment
Note on R73: Musson, Dean: responsible parties for event detection are either not communicated or ignored no documented processes for event detection across the board communication plan is not defined or consistent detection processes not continually improved
Note on S77: Musson, Dean: new incident response plan currently being drafted
Note on R79: Musson, Dean: incident response roles and responsibilities not socialized incident reporting more consistent, but some incidents continue to fall outside of consistent reporting; no documented process or policy no incident reponse tabletops performed or scheduled
Note on R82: Musson, Dean: events are more consistently investigated, but roles and responsibilities still blurred; infosec involved more than maybe we should be impacts of events are understood, but lack of process or policy forensic capabilities improved, but lack of documentation, process, strategy or policy
Note on S85: Musson, Dean: known incidents contained; some incident procedures exist mitigation plans against future incidents created through incident response; process adhoc and reactive
Note on S87: Musson, Dean: new response plan in draft process process improvement baked into incident response form and process
Note on R89: Musson, Dean: business continuity plan unknown business continuity plan not executed
Note on R91: Musson, Dean: business continuity plan, if one exists, is not reviewed or tested individual groups may have some strategies for business continuity, but no organizational effort seems to exist
Note on L92: Musson, Dean: CIP # 4 BCP - COOP
Note on R93: Musson, Dean: informal processes exist for the management of public or bureau relations